## Sheet1
task_name | description | due_date | priority | status | project_name | assigned_to | created_by | start_date | completion_date | comments
location | Identify suitable location and secure permissions | 2025-08-03 | Low | Completed | Annual Health Camp 2025 | vpe1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-07 | Contacted local authorities for required permissions — awaiting confirmation from Panchayat office.
staff | Coordinate with doctors and medical staff | 2025-08-03 | Low | Completed | Annual Health Camp 2025 | media@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-07 | Reached out to district hospital — 5 doctors and 8 nurses tentatively available for the camp dates.
pharmacy | Procure medical supplies and kits | 2025-08-03 | Low | Completed | Annual Health Camp 2025 | hello@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-06 | Prepared a list of essential medical supplies based on previous camps under review by the medical team
Patients Feedback | Volunteers assigned to each desk briefed on registration and query handling process | 2025-08-03 | Low | Completed | Annual Health Camp 2025 | gd1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-07 | Assigned volunteers to collect feedback at the exit point after check-up.
event | Schedule topics and speakers | 2025-08-04 | Low | Completed | Women Empowerment | writer@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-07 | Drafted a 6-month workshop calendar covering legal rights, financial literacy, digital skills, and entrepreneurship.
Medical Case for Save-Direct | Create 5 Medical Cse for Save-direct | 2025-08-28 | High | Completed | Child Help Foundation | wd1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-28 | 2025-08-28
promotions | Promote events via local NGOs | 2025-08-04 | Low | Completed | Women Empowerment | webteam@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-04 | 2025-08-04 | NGO partners agreed to mobilize women from nearby villages and SHGs (Self Help Groups)
certificates | Design and print certificates | 2025-08-04 | Medium | Completed | Women Empowerment | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-11 | Draft certificate design created — includes workshop title, participant name, date, and signatures of key organizers.
registrations | Track registrations and attendance | 2025-08-04 | Medium | Completed | Women Empowerment | webteam@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-04 | Created Google Form for online pre-registration — link shared with NGOs and on posters.
feedback | Collect workshop feedback | 2025-08-04 | Medium | Completed | Women Empowerment | institution@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-04 | Created online feedback form via Google Forms — shared QR code during closing session
metrics_dashboard | Create impact metrics dashboard | 2025-08-04 | High | Completed | Women Empowerment | hello@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 | 2025-08-05 | Identified key impact metrics — total participants, repeat attendance, topic ratings, and skill application rate.
course curriculum | Develop course curriculum and print materials | 2025-08-04 | Low | Not Started | Digital Literacy Program | media@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-01 |  | Outlined 12-week curriculum covering basic computer skills, internet safety, and MS Office tools
trainers | Onboard volunteer trainers | 2025-08-11 | Medium | In Progress | Digital Literacy Program | vpe1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-08 |  | Posted volunteer trainer requirement in local NGOs, community centers, and social media groups
enrolled students | Identify beneficiaries and enroll students | 2025-08-04 | Low | In Progress | Digital Literacy Program | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-11 |  | Created enrollment form capturing student details, education level, and contact information.
venue | Set up laptops and projectors at the venue | 2025-08-04 | Low | Not Started | Digital Literacy Program | vpe2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-06 |  | Tested all laptops for working condition, updated software, and installed required programs.
meetings | Conduct weekly review meetings | 2025-08-04 | Medium | Not Started | Digital Literacy Program | hello@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 |  | Scheduled weekly review meetings every Saturday evening with trainers and coordinators.
attendance | Track attendance and learning outcomes | 2025-08-04 | High | Not Started | Digital Literacy Program | wd2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 |  | Using attendance and assessment data to improve teaching methods and pacing.
reports | Submit monthly progress reports | 2025-08-04 | Low | Not Started | Digital Literacy Program | graphics@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-01 |  | Uploaded monthly report to shared drive and emailed to stakeholders.
NOC approvals | Finalize route and take police/NOC approvals | 2025-08-04 | Low | Completed | Fundraising Drive | institution@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-07 | Applied for NOC from police, municipal corporation, and sports authority — awaiting confirmation.
event poster | Create event poster and social media assets | 2025-08-04 | Medium | Completed | Fundraising Drive | media@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-04 | Designed event poster highlighting date, time, venue, and cause — theme colors inspired by hope and education
local gyms | Partner with local gyms and influencers | 2025-08-04 | Medium | Completed | Fundraising Drive | vpe1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-04 | Offered gyms free event passes for trainers in exchange for promoting to clients.
donation | Set up online ticketing and donation portal | 2025-08-04 | Low | Completed | Fundraising Drive | vpe2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-07 | Selected ‘Townscript’ platform for ticketing and Razorpay for donation processing.
kits | Distribute kits to runners | 2025-08-04 | Medium | Completed | Fundraising Drive | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-04 | Verified participant ID and registration before handing over kits.
volunteers | Coordinate volunteers for race day | 2025-08-04 | Medium | Completed | Fundraising Drive | wd2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-04 | Assigned team leaders for each functional area to streamline communication.
publish reports | Collect donations and publish report | 2025-08-04 | Low | Completed | Fundraising Drive | graphics@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-07 | Highlighted top contributors and corporate sponsors in the report.
awareness materials | Prepare presentation materials | 2025-08-05 | Low | In Progress | Environment Awareness Campaign | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 |  | Prepare the presentation materials for giving the awareness on environmental spaces
vists | Schedule school/college visits | 2025-08-31 | Low | In Progress | Environment Awareness Campaign | media@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-02 |  | Daily visiting the schools/colleges for giving the awareness
eco-friendly kits | Distribute pamphlets and eco-friendly kits | 2025-08-08 | High | In Progress | Environment Awareness Campaign | vpe2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 |  | Provide the pamphlets and eco-friendly kits for getting the awareness on Environment.
environmental feedback | Collect feedback from participants | 2025-08-31 | Medium | In Progress | Environment Awareness Campaign | institution@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-02 |  | To collect the feedback from trinees.
environment report | Submit final campaign report | 2025-08-04 | High | Completed | Environment Awareness Campaign | graphics@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-02 | 2025-08-07 | To generate the environmental reports for getting the awareness
content audit | Conduct content audit | 2025-08-08 | Low | In Progress | NGO Website Redesign | media@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-05 |  | Reviewed all existing website pages to assess relevance and clarity of content.
hiring | Hire or assign a designer and developer | 2025-08-09 | Low | In Progress | NGO Website Redesign | hello@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-05 |  | Interviewed and evaluated candidates based on portfolio, NGO experience, and communication skills.
case studies | Write new stories and case studies | 2025-08-09 | High | In Progress | NGO Website Redesign | writer@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-05 |  | Identified impactful beneficiary stories and successful projects to feature.
donations | Integrate donation and volunteer forms | 2025-08-10 | Low | In Progress | NGO Website Redesign | institution@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-05 |  | Linked donation form to secure payment gateway (e.g., Razorpay, Stripe, etc.) with success/failure redirects.
monitor analytics | Go live and monitor analytics | 2025-08-11 | High | In Progress | NGO Website Redesign | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-05 |  | Website successfully deployed to production environment on [insert go-live date].
ngo website feedback | Gather feedback and iterate | 2025-08-11 | Medium | In Progress | NGO Website Redesign | vpe2@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-05 |  | Collected feedback from internal team, donors, and volunteers via online form and interviews.
Annual Report 2025 | Please make sure it is done by thr time | 2025-08-11 | High | In Progress | Annual Health Camp 2025 | graphics@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-11
New Website Revamping | Revamping the existing website with a modern design, improved usability, and enhanced performance to deliver a better user experience. | 2025-08-27 | Low | In Progress | Child Help Foundation | vpe1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-11
Reposrt to SBF | Make Monthly Report | 2025-08-16 | High | In Progress | Child Help Foundation | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-11
All Region images update for the Annual Report | All Region images update for the Annual Report have to update in the Google Drive | 2025-08-16 | High | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-11
Child Help Foundation new Website images updates from the team | Child Help Foundation new Website images updates from the team | 2025-08-11 | High | In Progress | NGO Website Redesign | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-11
Newsletter update | Newsletter update | 2025-08-15 | Medium | In Progress | Child Help Foundation | vpe1@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-08-11
Payment update for Meta and GA _Campaigns Case Update for CHF: Update medical case information for Child Help Foundation (CHF) campaigns. | Payment update for Meta and GA _Campaigns Case Update for CHF: Update medical case information for Child Help Foundation (CHF) campaigns. | 2025-08-11 | Medium | Completed | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-11 | 2025-08-11
ABCD | AVDX | 2025-09-04 | Low | Not Started | Annual Health Camp 2025 | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-01
medical Case Image Upload | Need To Create | 2025-09-05 | High | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-05
Time pass |  | 2025-08-12 | High | In Progress | Child Help Foundation | hello@skypathdigital.com | hello@skypathdigital.com | 2025-08-12
Skypath Reel |  | 2025-08-12 | Low | Not Started | Child Help Foundation | gd1@skypathdigital.com | gd1@skypathdigital.com | 2025-08-12
Seprate Medical Case | Need to Create | 2025-08-12 | High | Completed | Child Help Foundation | wd2@skypathdigital.com | wd2@skypathdigital.com | 2025-08-12 | 2025-08-12 | Done
AAAAAAAABCD | ujkk | 2025-08-13 | Low | In Progress | Child Help Foundation | media@childhelpfoundationindia.org | media@childhelpfoundationindia.org | 2025-08-12
asdsfcfvc | bcv bc | 2025-08-12 | High | Completed | Child Help Foundation | vpe1@skypathdigital.com | vpe1@skypathdigital.com | 2025-08-12 | 2025-08-12 | cbcbcb
Newsletter for CA | kkjoijk | 2025-08-12 | High | Completed | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-08-12 | 2025-08-12
Banner for 15 August |  | 2025-08-13 | High | Completed | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-08-12 | 2025-09-04
* Accounts update for this - crm.childhelpfoundation.org/backend/* |  | 2025-08-21 | High | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-20
Share the all 11 Delhi Campaigns for Sanjay sinha and Team | Delhi Projects | 2025-08-21 | Medium | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-20
July Newsletter update | Newsletter update for Child Help Foundation | 2025-08-21 | Medium | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-20
4. Payment update for Meta and GA _Campaigns Case Update for CHF: Update medical case information for Child Help Foundation (CHF) campaigns. |  | 2025-08-20 | Medium | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-20
Feedback sharing for the Project Management tool for AI for Good |  | 2025-08-20 | Medium | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-08-20
medical Case Links | Need to Create | 2025-08-28 | High | Completed | Child Help Foundation | wd2@skypathdigital.com | wd2@skypathdigital.com | 2025-08-28 | 2025-08-28 | Done.
Uplaod Campaign Link in Filaantro | Need To Uplaod | 2025-08-28 | High | Completed | Fundraising Drive | wd2@skypathdigital.com | wd2@skypathdigital.com | 2025-08-28 | 2025-09-05 | Need To Uplaod
Need To Create Medical Case On CHF | Need To Create | 2025-09-04 | High | Completed | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-04 | 2025-09-04 | Need to Create
Chf Medical Images Updates | Need to Updates | 2025-09-04 | High | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-04 |  | Need To Update
Filaantro Campaign Created | Need to Create | 2025-09-04 | Medium | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-04
ID Card 203_13 |  | 2025-09-04 | Medium | Completed | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-09-04 | 2025-09-04
CHF ID Card 16 15 Anniversary Logo 4 Diary design 5 |  | 2025-09-01 | High | Not Started | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-09-01
CHF ID Card 2 + 16 15 Anniversary Logo 6 Anniversary word Diary design 5 LH 2 pg Bitosa Backdrop Bitosa ID Card | CHF ID Card 2 + 16 15 Anniversary Logo 6 Anniversary word Diary design 5 LH 2 pg Bitosa Backdrop Bitosa ID Card | 2025-09-02 | High | Completed | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-09-02 | 2025-09-04
CHF Punjab Flood Banner Himachal Flood Banner Bitosa Backdop Bitosa ID Card BItosa Check 3 + 5 names Biosa Backdop logo Bitosa Instagram 7 ID Card 96 | CHF Punjab Flood Banner Himachal Flood Banner Bitosa Backdop Bitosa ID Card BItosa Check 3 + 5 names Biosa Backdop logo Bitosa Instagram 7 ID Card 96 | 2025-09-03 | High | Completed | Child Help Foundation | graphics@skypathdigital.com | graphics@skypathdigital.com | 2025-09-03 | 2025-09-04
facebook ads google ads report | facebook ads google ads report | 2025-09-04 | Medium | Completed | facebook campaigns chf | digital@childhelpfoundationindia.org | media@childhelpfoundationindia.org | 2025-09-04 | 2025-09-04
VDJFDJDKJD | XVF | 2025-09-04 | Low | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-04
Medical case Uplaod | Need to Upload by Today | 2025-09-05 | High | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-05
Medical Case Uplaod in all Dashboard (Beti bachao Beti padhao) | Need To Create | 2025-09-05 | High | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | wd2@skypathdigital.com | 2025-09-05
sample | "this is sample task" | 2025-09-18 | Low | Not Started | Annual Health Camp 2025 | digital@childhelpfoundationindia.org | webteam@childhelpfoundationindia.org | 2025-09-18
mulitple assignees | sample 2 | 2025-09-18 | Low | Not Started | Annual Health Camp 2025 | webteam@childhelpfoundationindia.org, wd1@skypathdigital.com, content@skypathdigital.com | webteam@childhelpfoundationindia.org | 2025-09-18
Timeline for the Project and meeting with Yugal regarding the update | Asset Management Project | 2025-09-24 | High | In Progress | investment project | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-24
CA Payment update Details for the months |  | 2025-09-24 | Medium | In Progress | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-24
Content Calendar update for all |  | 2025-09-24 | Medium | Not Started | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-24
Donation update for Filaantro, CHF, CHF and SBF | Payment update for Meta and GA _Campaigns Case Update for CHF: Update medical case information for Child Help Foundation (CHF) campaigns. | 2025-09-24 | Medium | Completed | Child Help Foundation | digital@childhelpfoundationindia.org | digital@childhelpfoundationindia.org | 2025-09-24 | 2025-09-24
Calendar for New Year 2026 | Child Help Foundation Calendr Design content and Data update | 2025-09-27 | Medium | In Progress | Child Help Foundation | ppc@skypathdigital.com | digital@childhelpfoundationindia.org | 2025-09-24